## Slide 1: Web Strategy Weekly Update
September 12, 2012

## Slide 2: Agenda
Accomplishments, Goals, and Action Items by Track
Issues and Risks
Team Updates
Additional Topics as Needed
  Training Plan
  Communication Plan
  Dotnet Intranet Hub

## Slide 3: Site Preparation
Accomplishments:
  Scheduled executive review with Air Consumer
  Finalized training plan
  Created draft communication plan
  Created skeleton framework for Dotnet Intranet hub
Goals:
  Complete content entry for Air Consumer
  Complete additional content entry items for Policy (post-approval changes)
  Schedule executive review with 2 outstanding offices
  Execute refresher training courses
  Complete Dotnet Intranet hub
Action Items | Owner | Due | Status
Schedule OCIO Executive Review of site | Kristen, Francisco, Lauren | 9/5 | 

## Slide 4
Office | GA Profile Set Up | GA Guide Sent | GA Training | Follow Up/Custom Reports
DRC | √ Complete | Scheduled for 3/21 | Scheduled for 3/21 | Will contact post training
General Counsel | √ Complete | √ Complete | √ Complete | Email sent
Regulations | √ Complete | √ Complete | √ Complete | Email sent
OISER | √ Complete | √ Complete | √ Complete | Email sent
Air Consumer | √ Complete | √ Complete | √ Complete | Email sent
Public Affairs | √ Complete | √ Complete | √ Complete | Email sent
OCIO | √ Complete | √ Complete | √ Complete | Email sent
Budget | √ Complete | √ Complete | √ Complete | Email sent
ODAPC | √ Complete | √ Complete | √ Complete | Email sent
Policy | √ Complete | √ Complete | √ Complete | Email sent
OST Office Google Analytics Reporting

## Slide 5
Office | Executive Review | Content Entry | Training | Proposed Training Schedule
Government Affairs | √ Complete (7/10 Turner) | √ Complete |  | Go Live minus 2-3 weeks
Intelligence, Security, Emergency Response | √ Complete (7/3 Hines) | √ Complete |  | Go Live minus 2-3 weeks
Administration | √ Complete (8/3 LeFevre) | √ Complete |  | Trained in February. Refresher training Go Live minus 2-3 weeks.
Careers | √ Complete (7/11 Adams) | √ Complete |  | Go Live minus 2-3 weeks
Disability Resource Center | √ Complete (Burnham, Day) | √ Complete |  | Go Live minus 2-3 weeks
General Counsel | √ Complete (7/19 Rivkin) | √ Complete | √ Complete | Trained in February. No refresher needed, currently doing parallel updates.
Site Preparation – Office Approval & Training

## Slide 6: System Development & Site Infrastructure
Accomplishments:
  Conducted kickoff meeting and planning with Acquia
  Completed development on:
    Workflow segregation by category and office role
    Content archival
  Supported migration into Acquia enterprise development environment
Goals:
  Complete testing and bug fixing on:
    Workflow segregation
    Content archival
  Complete regression testing on site in Acquia enterprise development environment
Open Questions:
  Timeframe for security and performance audit by Acquia?

## Slide 7: Web Governance
Action Items | Owner | Due | Status
Provide template for governance policy to Dan | Lauren |  | 

## Slide 8: Future Phase Planning & Buy In
Accomplishments:
  Prioritize scope for next iteration
  Conducted demo for PHMSA Public Affairs
Goals:
  Refine iteration 2 scope and staffing
Open Questions:
  Other upcoming demos with modes?
Action Items | Owner | Due | Status
Facilitate introduction between Acquia and RITA | Francisco | 9/14 | 
Provide ‘sandbox’ through Acquia’s local dev environment to PHMSA | Brett | 9/14 | 

## Slide 9: Risk/Issue Tracker
Severe
Significant
Moderate
Low
Severity | Focus Area | Risk/ Issue Description | Last Update | Mitigation Path | Trend | Owner
 | C&A Approvals | Risk: Delays on C&A approvals for site could delay go live plans | 12 Sep 2012 Impact: H | Monitor C&A status and ensure support for the process is the top priority for those involved |  | Kristen, Lauren, Francisco
 | Security & Performance Audit | Risk: Any issues identified by security or performance audits will need to be addressed by the team by 9/30, which is currently unplanned work | 12 Sep 2012 Impact: H | Work with Acquia to understand any issues, and prioritize above planned work |  | Brett/Katie
 | Launch Resources | Risk: Due to delays on environment procurement, key resources must be coordinated for launch activities | 12 Sep 2012 Impact: M | Negotiate resources assuming a 9/30 go live date |  | Jodi/Katie
 | Content Updates | Risk: Go live preparation activities may impact the team’s ability to support end of fiscal year content updates | 12 Sep 2012 Impact: M | Plan for go live with Acquia asap, and communicate expectations to offices on timeframe for any content freeze |  | Katie/Mike R.
DOT Web Strategy Project Risks & Issues
Last Update: 12 September 2012
Steady
Excelling
Deteriorating
Improving
Key: Green Text= New Risk/Issue

## Slide 10: Team Updates
September Vacation Plans:
  Katie – 9/21

## Slide 11
  REFERENCE SLIDES

## Slide 12: Go Live: Critical Path Activities
# | Activity | Status | Owner | Level of Effort (Remaining)
1 | Acquia environment procurement | Complete | KB, FR, LB | 
2 | Site development and testing | In progress | Brett | 3 days
3 | Office content entry | In progress | Mike | 3 days
4 | Office executive review approval | In progress | Mike | 1 day
5 | Acquia preparation | Complete | Acquia | 
6 | Training | In progress | Mike | 3 days
7 | Acquia site audit | Not started | Acquia | 4 days
8 | External communication | Not started | KB, FR, LB | ?
9 | Pre-launch prep | Not started | Brett | 2 days
10 | Final content updates | Not started | Mike | 1 week
11 | Go live | Not started | Brett | 1 day